## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Harsh Raj | 2025-02-21 | Error with Post Processing Methods | S2 | Harsh Raj | wrong code | correct the code using gpt | 2025-02-21 | Closed | enhancing overall accurracy
2 | Harsh Raj | 2025-02-24 | Error with OCR text extraction accuracy | S2 | Harsh Raj | error in code | Adopted Post-processing techniques with corrected code | 2025-01-13 | Closed | Enhanced the accuarcy
3 | Harsh Raj | 2025-03-03 | Error with llm model fine-tuning | S6 | Harsh Raj | complexities | Utilized better versions for better performance | 2025-03-04 | Closed | better performance

## Sheet2
Logical
User Interface
Maintainability
Standards
Others